## Burndown Chart
Task | Story Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
database framework | 7 | 0 | 3 | 3 | 0 | 0 |  |  |  | 6
login form | 2 | 0 | 1 | 0.25 | 0.25 | 0.25 |  |  |  | 1.75
register form | 2 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 2
permissions | 4 | 0 | 0 | 0 | 0.5 | 0.5 |  |  |  | 1
class model | 1 | 0 | 0.25 | 0.25 | 0 | 0 |  |  |  | 0.5
class views (controller) | 1 | 0 | 0.25 | 0.25 | 0 | 0 |  |  |  | 0.5
lecturer/class permission | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
schedule form | 3 | 0 | 0.5 | 0.5 | 0 | 0 |  |  |  | 1
students in class in database | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
student access to class schedules | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
create exam timetable | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
assign student to time slots | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
date/time managed in database (program) | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
students loged in can access schedule | 2 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
multiple students can have the same timeslot up to set maximum | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
lecturers have permission to edit timeslots | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
lectureres have permission to reset student passwords | 3 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Actual Remaining Effort | 27 | 27 | 21 | 16.25 | 15 | 14.25 | 14.25 | 14.25 | 14.25
Estimated Remaining Effort | 27 | 23.625 | 20.25 | 16.875 | 13.5 | 10.125 | 6.75 | 3.375 | 0

## Product Backlog
User Stories | Tasks | Task Story Points | User Story Story Points | Sprint 1.5 Priority | Sprint 2.0 Priority | Sprint 2.5 Priority | Sprint 3.0 Priority | Sprint 3.5 Priority | Sprint 4.0 Priority | Sprint 4.5 Priority
As a lecturer I want to have an application that supports multiple user types ('student' and 'admin') so that different user types have different privileges | Database Framework | 7 | 15 | 1 | 1 | 1 | 1 | 1
| Login Form | 2
| Register Form | 2
| Permissions | 4
As a lecturer I want to have a class created for each course so that all courses can have their own information/resources | Class Model | 1 | 2 | 2 | 2 | 2 | 2 | 2
| Class Views (controller) | 1
As a lecturer I want to have a lecturer assigned to each class so that the lecturer can set schedules for that class | Lecturer Class Permission | 2 | 5 | 3 | 3 | 3 | 3 | 3
| Schedule Form | 3
As a lecturer I want to enrol students in classes so that the students can access the class schedules | Students in Class in Database | 4 | 5 | 4 | 4 | 4 | 4 | 4
| Student access to Class Schedules | 1
As a lecturer I want to create Test/Presentation Schedules and time slots so that they are viewable to the students | Create Exam Timetable | 3 | 6 | 5 | 5 | 5 | 5 | 5
| Assign Student to Time Slots | 3
As a lecturer I want to have customizable time slots for a date so that the lecturer can see the available time slots | Date/Time managed in Database (program) | 5 | 5 | 6 | 6 | 6 | 6 | 6
As a student I want to access the Test/Presentation Schedule so that I can pick an appropriate time slot | Students logged in can access Schedule | 2 | 5 | 7 | 7 | 7 | 7 | 7
| Multiple Students can have the same Time Slot up to set max | 3
As a lecturer I want to be able to remove students from time slots so that the student can select different time slots | Lecturers have Permission to edit Time Slots | 3 | 3 | 8 | 8 | 8 | 8 | 8
As a lecturer I want to reset any student's application password so that students can access their accounts | Lecturers have Permission to reset Student Passwords | 3 | 3 | 9 | 9 | 9 | 9 | 9